## Project schedule
| Website project |  |  |  |  | Project start: | [7 empty] | 2025-01-01
Prepared by Kevin Molina
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html |  |  |  |  | 2025-01-01 | [6 empty] | 2025-01-08 | [6 empty] | 2025-01-15 | [6 empty] | 2025-01-22 | [6 empty] | 2025-01-29 | [6 empty] | 2025-02-05 | [6 empty] | 2025-02-12 | [6 empty] | 2025-02-19 | [6 empty] | 2025-02-25 | [6 empty] | 2025-03-05 | [6 empty] | 2025-03-12 | [6 empty] | 2025-03-19 | [6 empty] | 2025-03-26 | [6 empty] | 2025-04-02 | [6 empty] | 2025-04-09 | [6 empty] | 2025-04-16
| TASK | ASSIGNED TO | START | END | time axis 2025-01-01 to 2025-04-22
 | time axis 2025-01-01 to 2025-04-22
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Research & Analysis | Earnstky Louis | 2025-01-01 | 2025-01-10 | 10 | 2025-01-01: Local host configured
| Design Phase | Nathaniel Carrasquillo | 2025-01-11 | 2025-01-20 | 10 | 2025-01-11: MySQL DBMS configured
| Development Phase | Nathaniel Carrasquillo | 2025-01-21 | 2025-03-10 | 49 | 2025-01-21: TomCat server configured; 2025-01-30: Model, View, Controller configured
| Testing & QA | Kevin Molina | 2025-03-11 | 2025-04-11 | 32 | 2025-03-11: Testing MySQL; 2025-03-20: Testing the site; 2025-03-27: Testing code
| Launch & Post-launch support | Nathaniel Carrasquillo | 2025-04-20 | Ongoing | #VALUE!