## Sheet1
Team Member Name | Roles | Task | Objective | Deadline | Dependencies | Completion Status
Nathaniel Carrasquillo | Computer Network Engineer/Sys Admin | Configure the host/server by running Windows updates, adding antivirus (AV), setting up a VPN, installing RMM software, and enabling SSH access. Configure the local network to open ports 443 and 22 for public and remote access. Install IntelliJ IDEA (IDE) and configure it on the local host. Configure MySQL and foundation of the backend using IntelliJ IDEA. | To configure the local host/server. | 2025-01-26 | N/A | In Progress
Kevin Molina | Frontend developer | Design the website's UX/UI using HTML and CSS, keeping the experience simple and user-friendly | To design the website's UX/UI | 2025-01-26 | [Any dependencies] | In progress
Ernstky Louis | Frontend/ ui/ux researcher | Research and design an inuitive and user-friendly ui/ux website. assist with html/css edits or debugging if needed. conduct user feedback sessions to improve the design | ensure the website provides a seamless and visually appealing experience for users. | 2025-01-26 | [Any dependencies] | in progress
[Team Member Name 2] | [Role 2] | [Task 1 Description] | [Brief Task Objective] | [Date] | [Any dependencies] | [Not Started/In Progress/Completed]